## Taskboard
Taskboard
User Story | To Do | In Progress | Done
As a user, I want the gap to be able to work on any sized android screen so that I know it will be visually presentable on my device |  |  | App/Game is compatible for different screen sizes
As a player, I want the game to work and tiles to more properly. |  |  | Game Functionality
As a player, I want the game to end so that I know exactly when I have successfully solved the puzzle. | Determine if puzzle is solved
As a player, I want the application to have a main menu as the screen that pops up first when I open the app so that I have options before starting a game | Main Menu
As a beginner, I want there to be a section that explains how to play the game so that I can understand what I am supposed to do, and I know the objective of the puzzle | How-To-Play section
As a player, I want to see the tile actually move into place instead of appearing into place so that the puzzle isn't as boring. | Animated tile movement
As a competitor, I want to know the current time I’ve spent on the puzzle and the amount of moves that I’ve done so that I know my current statistics for this puzzle and can keep track of how well I am doing | Time keeping
Move Counter
As a competitor, I want the application to keep track of my best times and move counts for the puzzles so that I can keep track of my best times and try to beat them | High Score tracking
High Score section in the Main Menu
As a player, I want to actually be given a slider puzzle that can be solved so that I don’t have to worry about wasting my time, doing the puzzle just to see that the board given to me isn’t playable or solvable | Check if given puzzle is solvable or not
As a novice puzzle player, I want to be able to choose a different board size for the puzzle so that I can not only have more variety in the puzzle, but also be challenged with a larger and harder version of the puzzle | Add different difficulties/board sizes
As a player, I want to be able to play a slider puzzle that uses pieces besides numbered tiles so that I can get a bit more variety from the app and customize the puzzle, so it isn’t the same every time | Use a picture instead of numbered tiles

## To-Do List
To-Do List
Category | Task # | Est. Hours | Description
Prework | 10 | 1 | Install Android Studio IDE
Must Do | 100 | 4 | Make the game board adaptable to all screen sizes
| 200 | 2 | Add the game logic
| 210 | 1 | Determine if the current puzzle board is solved or not
| 220 | 2 | Only give a solvable puzzle to play
| 300 | 1 | Build the Main Menu
| 310 | 1 | Add a How-To-Play section
| 230 | 1 | Add a timer to the puzzle
| 240 | 1 | Add a move counter
| 320 | 2 | Keep track of High Scores
| 330 | 2 | Add a High Score section to Main Menu
Should Do | 250 | 2 | Animate the tile pieces moving
| 260 | 3 | Add option for different sized puzzle boards
| 270 | 4 | Option for using a picture instead of numbered tiles
Would Like | 280 | 1 | Tile animation sound
| 290 | 1 | Background music
| 340 | 1 | Volume setting in menu